## Updated Plan for v.1.6
| S9 |  |  |  |  | S10 | [12 empty] | S11 | [13 empty] | S12 | [13 empty] | S13 | [13 empty] | S14 | [13 empty] | S15
| 2019-05-09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 2019-06-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 2019-07-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Gigi + Mike (Wireframe + User Story) | A,C,D,DD |  |  |  |  | B,I | [5 empty] | H Part 1 |  |  | H Part 2 |  |  |  | JJ, | [5 empty] | 3: O,FF; S12 10: AA,GG; S12 17: W,Z; S13 24: CC
William + Mike (Wireframe + User Story) | E,F,G, J,L,M |  |  |  |  | P,Q | [5 empty] | R | [6 empty] | MM,K, ZZ* | [5 empty] | 3: S,KK,U,V,ZZ*; S12 10: N,LL; S12 17: NN,T,X,Y; S13 24: BB |  | HH,II | [14 empty] | william away
| A | Customer Profile login + Profile (Post-logon) | [17 empty] | AA | Password Reset Page (Customer Portal)
| B | Customer Profile login (AppID+BR combination) | [17 empty] | FF | Reactivate Profile
| C | Create Profile (Pre-logon) | [17 empty] | GG | User name retreival
| D | Old Profile 2nd password creation | [17 empty] | BB | Document Archival
| E | Admin Portal | [17 empty] | HH | Export to excel (MI)
| F | Question Set (Table) | [17 empty] | II | MI Report
| G | Workflow (Mass RP) | [17 empty] | CC | Print Offline form
| DD | One-time password generation and verification | [17 empty] | KK | SOP API Integration part 1 |  |  |  | S12 10: (involve other systems)
| H | Customer Facing Form (200 Questions) | [17 empty] | LL | API Integration |  |  |  | S12 10: (involve other systems)
| I | Application Status portal (Post-logon/AppID + BR) | [17 empty] | MM | Personal Calendar |  |  |  | S12 10: (scope not available)
| J | Create Application (MassRP) | [17 empty] | NN | Customer view |  |  |  | S12 10: (how to do this?)
| K | Access Control
| L | Form Comment | [17 empty] | ZZ | S5/6/9/10/11 Refine
| M | Handling Staff
| N | Document Management (Staff)
| O | Document Management (Customer)
| P | Calendar - Create / Edit Appointment
| Q | Manage Timeslot
| R | Workflow (RM)
| S | Email (Function Enhancement after ICCM integration)
| T | Print Form (Staff Full Version)
| U | Workflow (ETB) | [9 empty] | (6 flows)
| V | Notification (function structure design)
| W | Offline Form (1200 question)
| X | Print Form (Other Version)
| Y | Audit and Track 1,2,3
| JJ | Customer Workflow
| EE | Offline Form (Customer Facing)
| Z | Offline Form upload

## backup
| S9 |  |  |  |  | S10 | [12 empty] | S11 | [13 empty] | S12 | [13 empty] | S13 | [13 empty] | S14 | [13 empty] | S15
| 2019-05-09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 2019-06-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 2019-07-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Gigi + Mike (Wireframe + User Story) | A,C,D,DD |  |  |  |  | B,I | [5 empty] | H Part 1 |  |  | H Part 2 |  |  |  | JJ, | [5 empty] | 3: O,FF; S12 10: AA,GG; S12 17: W,Z; S13 24: CC
William + Mike (Wireframe + User Story) | E,F,G, J,L,M |  |  |  |  | P,Q | [5 empty] | R | [6 empty] | MM,K, ZZ* | [5 empty] | 3: S,KK,U,V,ZZ*; S12 10: N,LL; S12 17: NN,T,X,Y; S13 24: BB |  | HH,II | [14 empty] | william away
| A | Customer Profile login + Profile (Post-logon) | [17 empty] | AA | Password Reset Page (Customer Portal)
| B | Customer Profile login (AppID+BR combination) | [17 empty] | FF | Reactivate Profile
| C | Create Profile (Pre-logon) | [17 empty] | GG | User name retreival
| D | Old Profile 2nd password creation | [17 empty] | BB | Document Archival
| E | Admin Portal | [17 empty] | HH | Export to excel (MI)
| F | Question Set (Table) | [17 empty] | II | MI Report
| G | Workflow (Mass RP) | [17 empty] | CC | Print Offline form
| DD | One-time password generation and verification | [17 empty] | KK | SOP API Integration part 1 |  |  |  | S12 10: (involve other systems)
| H | Customer Facing Form (200 Questions) | [17 empty] | LL | API Integration |  |  |  | S12 10: (involve other systems)
| I | Application Status portal (Post-logon/AppID + BR) | [17 empty] | MM | Personal Calendar |  |  |  | S12 10: (scope not available)
| J | Create Application (MassRP) | [17 empty] | NN | Customer view |  |  |  | S12 10: (how to do this?)
| K | Access Control
| L | Form Comment | [17 empty] | ZZ | S5/6/9/10/11 Refine
| M | Handling Staff
| N | Document Management (Staff)
| O | Document Management (Customer)
| P | Calendar - Create / Edit Appointment
| Q | Manage Timeslot
| R | Workflow (RM)
| S | Email (Function Enhancement after ICCM integration)
| T | Print Form (Staff Full Version)
| U | Workflow (ETB) | [9 empty] | (6 flows)
| V | Notification (function structure design)
| W | Offline Form (1200 question)
| X | Print Form (Other Version)
| Y | Audit and Track 1,2,3
| JJ | Customer Workflow
| EE | Offline Form (Customer Facing)
| Z | Offline Form upload

## old
[8 empty] | S10 | [12 empty] | S11
|  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | Gigi | 9: S8 wireframe; S10 16: S9 wireframe; S10 24: S10 wireframe
|  | Mike | 9: S8 user story; S10 16: S9 user story; S10 24: S10 user story
|  | Vilit | S10 16: S8 html prototype; S10 24: S9 html prototype; S11 3: S10 html prototype
|  | Alfred | S10 24: S8 Development; S11 3: S9 Development; S11 10: S10 Development
Give to development
S8 | Customer Profile login + Profile (Post-logon) | bar: 10
Customer Profile login (AppID+BR combination) | bar: 10
Create Profile (Pre-logon) | bar: 10
S9 | Customer Facing Form (200 Questions) |  | S10 22: P1; S11 29: ALL
Admin Portal | bar: S10 16
S10 | Application Status portal (Post-logon/AppID + BR) | bar: S10 17
Handling staff | bar: S10 20
Comment | bar: S10 20
S11
S12
S13